## Sheet1
Logbook project | [6 empty] | Asset Store things used | Libraries used | Oopsy Daisies
Task | Date start | Date finish | Deadline | Note |  |  |  |  | Deleted all scripts 11/02/2017
Find potential projects | 09/20/2016 | 2016-06-10 | Yes - Same as finish date | Ask supervisor if they are ok as well as decide by deadline
Write a project proposal | 2016-08-10 | 10/20/2016 | Yes - Same as finish date | Architecture diagrams and a description about the project
Research Unity | 2016-08-10 | N/A | N/A | As I will be learning how to use Unity as I go along there isn't really a finish date
Watch tutorials and learn how to use Unity | 2016-08-10 | N/A | N/A | As I will be learning how to use Unity as I go along there isn't really a finish date
Practise using Unity | 2016-08-10 | N/A | N/A | As I will be using Unity for pretty much the whole project there isn't really a finish date
Add movement to a ball | 10/15/2016 | 10/20/2016 | N/A | Added movement of a ball
Add collision detection | 10/15/2016 | 10/20/2016 | N/A | Added collision detection so that it wouldn't go through walls
Add gravity | 10/15/2016 | 10/20/2016 | N/A | Can now fall
Added picking up items | 10/21/2016 | 10/25/2016 | N/A | Can now pick up yellow "coins" off the ground
Added my own prefabs | 10/25/2016 | 10/26/2016 | N/A | Basically objects that I designed, made a door and a chair
Added a wall | 10/26/2016 | 10/31/2016 | N/A | Added a wall to celebrate triumph
Added blocks | 10/26/2016 | 10/31/2016 | N/A | Added blocks, and more design stuff; You can jump on these things to collect the coins
Added first person | 2016-01-11 | 2016-06-11 | N/A | Added looking up, down, left right, diagonal
Add the ability to pick up things | 2016-07-11 |  |  | Can literally pick up the world, so a bit buggy, not high on priority to fix
Add hills with textures | 11/15/2016 | 11/18/2016
Add start menu | 11/23/2016 | 11/28/2016 |  | A start menu that you can click on start to start game
Fix guard | 01/15/2017 |  |  | Still broken, game crashes when player moves near guard - removed for now
Mountain climbing | 01/15/2017 |  |  | Trying to fix where the player can climb up mountain with space spam
Add inventory | 11/23/2016
Add save game option | 11/30/2016
Added day night cycle | 01/20/2017 | 01/25/2017 |  | Added a day night cycle, time taken to do a full day night cycle can now be changed
Added signs | 2017-10-02 | 2017-10-02 |  | Added tutorial signs that players can look at, no text added yet,fixed a bug where sign would fall over | Text on signs broken
Dialogue boxes added | 2017-11-02 | 02/15/2017 |  | NPC dialogue added, need to disable movement when talking to NPC | Movement broken | Fixed
Guard kind of fixed | 02/19/2017 | 02/20/2017 | N/A | Need to make guard stop a bit away and stop all movement, as at the moment the guard will be humping leg
Made map look better, changed a few of the mountains | 2017-05-03 | 2017-10-03 |  | Simply trying to pretty up the map
Added a "stage" | 03/20/2017 | 03/25/2017 |  | Added a labyrinth into the stage will add more
Switch scene on objective completion | 03/27/2017