## Sheet1
Logbook project
Task | Date start | Date finish | Deadline | Note
Find potential projects | 09/20/2016 | 2016-06-10 | Yes - Same as finish date | Ask supervisor if they are ok as well as decide by deadline
Write a project proposal | 2016-08-10 | 10/20/2016 | Yes - Same as finish date | Architecture diagrams and a description about the project
Research Unity | 2016-08-10 | N/A | N/A | As I will be learning how to use Unity as I go along there isn't really a finish date
Watch tutorials and learn how to use Unity | 2016-08-10 | N/A | N/A | As I will be learning how to use Unity as I go along there isn't really a finish date
Practise using Unity | 2016-08-10 | N/A | N/A | As I will be using Unity for pretty much the whole project there isn't really a finish date
Add movement to a ball | 10/15/2016 | 10/20/2016 | N/A | Added movement of a ball
Add collision detection | 10/15/2016 | 10/20/2016 | N/A | Added collision detection so that it wouldn't go through walls
Add gravity | 10/15/2016 | 10/20/2016 | N/A | Can now fall
Added picking up items | 10/21/2016 | 10/25/2016 | N/A | Can now pick up yellow "coins" off the ground
Added my own prefabs | 10/25/2016 | 10/26/2016 | N/A | Basically objects that I designed, made a door and a chair
Added a wall | 10/26/2016 | 10/31/2016 | N/A | Added a wall to celebrate triumph
Added blocks | 10/26/2016 | 10/31/2016 | N/A | Added blocks, and more design stuff; You can jump on these things to collect the coins
Added first person | 2016-01-11 | 2016-06-11 | N/A | Added looking up, down, left right, diagonal
Add the ability to pick up things | 2016-07-11 |  |  | Can literally pick up the world, so a bit buggy, not high on priority to fix
Add hills with textures | 11/15/2016 | 11/18/2016
Add start menu | 11/23/2016 | 11/28/2016 |  | A start menu that you can click on start to start game
Fix guard | 01/15/2017
Mountain climbing |  |  |  | Trying to fix where the player can climb up mountain with space spam
Add inventory | 11/23/2016
Add save game option | 11/30/2016